## KG-MIS Overview
KG-MIS — COMBINED REPORTING, LANGUAGE & DATE-CASCADING MODEL
Reporting Model | Primary Purpose | Input Source | Key Deliverables | Period Start | Period End | Planned Submission | Next Reporting Date | Status | Owner
Weekly | Rapid market and competitor intelligence | Field data, competitor prices, weekly sales, customer feedback | Weekly MI Report; Competitor Update; Sales Trend; Alerts | 2026-09-07 | 2026-09-13 | 2026-09-14 | 2026-09-14 | Ongoing | Marketing Intelligence
Monthly | Consolidated performance and market analysis | Weekly reports + monthly sales + customer/competitor inputs | Monthly MI Report; Sales Performance; Product Performance; Customer & Competitor Insight | 2026-09-01 | 2026-09-30 | 2026-10-04 | 2026-10-01 | Planned | Marketing Intelligence
Quarterly | Strategic trend and gap analysis | Three monthly reports + quarterly market/brand review | Quarterly Market & Competitor Analysis; Brand Review; Regional/Opportunity Analysis | 2026-07-01 | 2026-09-30 | 2026-10-10 | 2026-10-01 | Planned | Marketing Intelligence
Annual | Full-year strategic intelligence and planning support | Four quarterly reports + annual sales/market/brand data | Annual MI Report; Annual Market Share; Annual Sales & Brand Review; Strategic Recommendations | 2026-01-01 | 2026-12-31 | 2027-01-31 | 2027-01-01 | Planned | Marketing Intelligence
DATE CASCADING LOGIC
Weekly → Monthly | Every weekly report feeds the corresponding monthly report.
Monthly → Quarterly | Three monthly reports feed the quarterly analysis.
Quarterly → Annual | Four quarterly reports feed the annual strategic report.
Status Tracking | Not Started / In Progress / Under Review / Completed / Delayed / Ongoing / Planned

## Master Schedule
KG-MIS MASTER WORK PLAN — SEPTEMBER 2026
Week | Date Range | Month | Main Focus | Detailed Activity | Reporting Model | Period Start | Period End | Planned Submission Date | Actual Submission Date | Status | Responsible | Key Deliverable
Week 9 | 07 Sep – 13 Sep 2026 | Sep | Data Collection | Gather field data, competitor pricing, sales figures and market observations. Define KG-MIS multilingual requirements for English, Amharic and Afaan Oromo. | Weekly | 2026-09-07 | 2026-09-13 | 2026-09-14 |  | In Progress | Marketing Intelligence | Weekly data pack + language requirements matrix
Week 10 | 14 Sep – 20 Sep 2026 | Sep | Analysis & Drafting | Analyze collected data and draft recurring reports. Prepare language structure and standardized translation dictionary for menus, forms, surveys, alerts and reports. | Weekly | 2026-09-14 | 2026-09-20 | 2026-09-21 |  | Planned | Marketing Intelligence + ERP/System Team | Draft weekly reports + multilingual terminology dictionary
Week 11 | 21 Sep – 27 Sep 2026 | Sep | Review & Periodic Deliverables | Review drafts for accuracy; conduct competitor, customer, market trend, brand, regional, distribution and product-gap analyses. Validate multilingual interface and data-entry logic. | Weekly / Quarterly | 2026-09-21 | 2026-09-27 | 2026-09-28 |  | Planned | Marketing Intelligence + Selected Users | Reviewed reports + UAT language validation + quarterly analytical inputs
Week 12 | 28 Sep – 04 Oct 2026 | Sep | Finalize & Submit | Finalize and submit September recurring reports and periodic deliverables. Finalize KG-MIS language package and submit to ERP/System Development. | Weekly / Monthly | 2026-09-28 | 2026-10-04 | 2026-10-04 |  | Planned | Marketing Intelligence + ERP/System Team | September report package + approved language implementation package

## Reporting Calendar
KG-MIS REPORTING CALENDAR — WEEKLY, MONTHLY, QUARTERLY & ANNUAL
Reporting Model | Report / Output | Period Start | Period End | Planned Submission Date | Actual Submission Date | Next Reporting Date | Feeds Into | Status | Responsible Person | Approval / Review | Remarks
Weekly | Weekly MI Report — W9 | 2026-09-07 | 2026-09-13 | 2026-09-14 |  | 2026-09-21 | September Monthly Report | In Progress | MI Officer | MI Manager
Weekly | Weekly MI Report — W10 | 2026-09-14 | 2026-09-20 | 2026-09-21 |  | 2026-09-28 | September Monthly Report | Planned | MI Officer | MI Manager
Weekly | Weekly MI Report — W11 | 2026-09-21 | 2026-09-27 | 2026-09-28 |  | 2026-10-04 | September Monthly Report | Planned | MI Officer | MI Manager
Weekly | Weekly MI Report — W12 | 2026-09-28 | 2026-10-04 | 2026-10-04 |  | 2026-10-12 | September Monthly Report | Planned | MI Officer | MI Manager
Monthly | September 2026 MI Report | 2026-09-01 | 2026-09-30 | 2026-10-04 |  | 2026-11-01 | Q3 2026 Report | Planned | MI Team | Corporate Marketing Manager | Consolidates weekly reports
Monthly | October 2026 MI Report | 2026-10-01 | 2026-10-31 | 2026-11-01 |  | 2026-12-06 | Q4 2026 Report | Planned | MI Team | Corporate Marketing Manager
Monthly | November 2026 MI Report | 2026-11-01 | 2026-11-30 | 2026-12-06 |  | 2027-01-03 | Q4 2026 Report | Planned | MI Team | Corporate Marketing Manager
Monthly | December 2026 MI Report | 2026-12-01 | 2026-12-31 | 2027-01-03 |  | 2027-02-07 | Q4 2026 / Annual Report | Planned | MI Team | Corporate Marketing Manager
Quarterly | Q3 2026 Market & Competitor Analysis | 2026-07-01 | 2026-09-30 | 2026-10-10 |  | 2027-01-10 | 2026 Annual Report | Planned | MI Team | Management | Jul–Sep
Quarterly | Q4 2026 Market & Competitor Analysis | 2026-10-01 | 2026-12-31 | 2027-01-10 |  | 2027-04-10 | 2026 Annual Report | Planned | MI Team | Management | Oct–Dec
Annual | 2026 Annual Market Intelligence Report | 2026-01-01 | 2026-12-31 | 2027-01-31 |  | 2028-01-31 | 2027 Strategic Planning | Planned | MI Manager | Senior Management | Full-year strategic report

## Reference Lists
KG-MIS STATUS, FREQUENCY & DATE-CASCADING REFERENCE
Status | Meaning | Reporting Model | Cascade Rule | Standard Frequency
Not Started | Activity has not yet begun | Weekly | Feeds monthly report | Every week
In Progress | Work has started and is currently being executed | Monthly | Consolidates weekly reports and feeds quarter | Every month
Under Review | Draft/report is completed and awaiting validation or approval | Quarterly | Consolidates three monthly reports and feeds annual | Every quarter
Completed | Activity/report has been finalized and submitted | Annual | Consolidates four quarterly reports | Every year
Delayed | Activity has passed the planned completion date
Ongoing | Recurring activity that continues regularly
Planned | Scheduled for a future reporting period