IT Department (Solution Development)

Hybrid Market Intelligence System (MIS)

Phase 0 — Project Planning Package

Project Code: KG-MIS-2026-DEV-PROPOSAL

| Field | Detail |
| --- | --- |
| Project Sponsor | Marketing Department, Kerchanshe Group |
| Requesting Officer | Mr. Tsegaye Nigusie — Marketing Intelligence Officer |
| Delivery Owner | IT Department (Solution Development) |
| CTO | Mr. Melkamu Alamerew |
| Project Manager | Mr. Estifanos Alemseged |
| Developer | Mr. Woluman Urgesa |
| QA/Test Engineer | Mr. Hirko Gemechu |
| Document Status | Draft v1.2 — For Review |
| Prepared Date | 24 July 2026 |

# Table of Contents

Table of Contents	2

1. Project Charter	4

1.1 Purpose	4

1.2 Business Justification	4

1.3 Project Objectives	4

1.4 High-Level Scope	4

1.5 Success Criteria	4

1.6 Timeline & Budget (Indicative)	4

1.7 Authorization	5

2. Business Case	6

2.1 Problem Statement	6

2.2 Proposed Solution	6

2.3 Expected Benefits	6

2.4 Budget Breakdown	6

2.4.1 Labor Cost	6

2.4.2 Infrastructure & Systems	6

2.4.3 Contingency	7

2.4.4 Total Estimated Budget	7

2.5 Risk of Not Proceeding	7

3. Scope Definition	8

3.1 In-Scope	8

3.2 Out-of-Scope (This Release)	8

3.3 Assumptions	8

3.4 Constraints	8

3.5 Phase 0 Deliverables	8

4. Stakeholder Identification	10

5. Team Formation	11

5.1 Project Team	11

5.2 Reporting Structure	11

6. Product Backlog Creation	12

6.1 Epics	12

6.2 Sample User Stories	12

6.3 Backlog Grooming	12

7. Sprint Planning — Sprint 0	13

7.1 Objective	13

7.2 Key Activities	13

7.3 Exit Criteria	13

8. Project Plan	14

8.1 Delivery Approach	14

8.2 Phase Overview (6 Weeks)	14

9. Sprint Roadmap	15

10. Risk Register / Risk Assessment	16

11. Communication Plan	17

12. Project Schedule	18

# 1. Project Charter

## 1.1 Purpose

This charter authorizes the Hybrid Market Intelligence System (MIS) project. It confirms delivery using the in-house team's existing skills (Node.js, Next.js, Express, MS SQL Server, TypeScript), with Power BI for analytics and integration with three internal systems: D365FO (ERP/CRM data), CUAS (role-based access), and CNS (notifications).

## 1.2 Business Justification

Market data — competitor pricing, distributor feedback, and field surveys — is currently collected manually and is hard to consolidate. The MIS will bring this data into one system, connected to the tools the business already uses, so Marketing can act on it faster.

## 1.3 Project Objectives

- Give Marketing one web portal to capture market visit reports and structured surveys.

- Capture and compare competitor pricing against our own.

- Provide Power BI dashboards and simple automated reports.

- Connect to D365FO for customer, sales, and product data.

- Use CUAS for user login and role-based access instead of building this from scratch.

- Use CNS for notifications (email, SMS, WhatsApp).

## 1.4 High-Level Scope

In scope: web admin portal, survey builder, competitor pricing module, Power BI dashboards, and integration with D365FO, CUAS, and CNS.

Out of scope for this release (Future Phase): the React Native mobile app, offline data collection, photo/video capture, GPS/location tracking, push notifications, barcode/QR scanning, a full CRM replacement, an automated pricing-decision engine, and a custom report builder beyond Power BI (CNS notifications remain limited to email, SMS, and WhatsApp).

## 1.5 Success Criteria

- System is live and Marketing users are submitting data through the web portal.

- Power BI dashboards show field and D365FO data correctly.

- Login/access works through CUAS and notifications work through CNS.

- Marketing Department signs off after user acceptance testing.

## 1.6 Timeline & Budget (Indicative)

| Item | Estimate | Notes |
| --- | --- | --- |
| Target Start Date | 27 July 2026 | Pending charter approval |
| Duration | 6 weeks (excluding Sundays) | See Project Plan, Section 8 |
| Budget | $3,054 | See detailed Budget Breakdown, Section 2.4 |

## 1.7 Authorization

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Ms. Mekdes Tilahun |  |  |
| CTO | Mr. Melkamu Alamerew |  |  |
| IT Solution Head/Manager | Mr. ______________ |  |  |
| Project Manager | Mr. Estifanos Alemseged |  |  |

# 2. Business Case

## 2.1 Problem Statement

Competitor pricing, distributor feedback, and field survey data are collected manually today. This is slow, inconsistent, and disconnected from D365FO and Power BI, which delays pricing and marketing decisions.

## 2.2 Proposed Solution

A single system for field data collection, competitor pricing, surveys, and reporting — built in-house, connected to D365FO for master data, CUAS for access control, and CNS for notifications.

## 2.3 Expected Benefits

- Faster, more consistent market intelligence reporting.

- Better pricing and marketing decisions from competitor benchmarking.

- One login and access system (CUAS) instead of a separate one for this app.

- Automatic notifications (CNS) instead of manual follow-ups.

- Lower cost and faster delivery by using the in-house team and existing internal systems.

## 2.4 Budget Breakdown

The breakdown below covers all resources needed to deliver the 6-week plan in Section 8. Person-week counts follow the Team Formation in Section 5. Currency amounts are marked TBD for Finance/IT to confirm using actual internal rates; the quantities and structure are fixed so the total can be completed quickly.

## 2.4.1 Labor Cost

| Role | Allocation | Duration | Est. Weekly Rate (USD) | Est. Cost (USD) |
| --- | --- | --- | --- | --- |
| Project Manager | Full-time | 6 weeks | $138 | $828 |
| Requirement Gathering & System Architecture | Full-time | 1 week | $113 | $113 |
| Backend Developer (Node.js/Express) | Full-time | 3 weeks | $126 | $378 |
| Frontend Developer (Next.js) | Full-time | 3 weeks | $113 | $339 |
| QA / Test Engineer (Hirko Gemechu) | Full-time | 2 weeks | $88 | $176 |
| Labor Subtotal |  | 15 person-weeks |  | $1,834 |

## 2.4.2 Infrastructure & Systems

| Item | Notes | Est. Cost (USD) |
| --- | --- | --- |
| Hosting (Development, Staging & Production) | Cloud hosting & MS SQL Server | $377 |
| D365FO Integration | Internal API configuration | $126 |
| CUAS Integration | Authentication integration | $94 |
| CNS Integration | Email, SMS & WhatsApp configuration | $157 |
| Power BI Configuration | Dashboard configuration | $94 |
| Domain, SSL & Development Tools | SSL, domains, miscellaneous tools | $94 |
| Infrastructure Subtotal |  | $942 |

## 2.4.3 Contingency

| Item | Basis | Est. Cost (USD) |
| --- | --- | --- |
| Contingency Reserve | 10% of Labor + Infrastructure | $278 |

## 2.4.4 Total Estimated Budget

| Category | Est. Cost (USD) |
| --- | --- |
| Labor Subtotal | $1,834 |
| Infrastructure Subtotal | $942 |
| Contingency (10%) | $278 |
| Total Estimated Budget | $3,054 |

## 2.5 Risk of Not Proceeding

Without the MIS, Marketing continues to rely on manual, fragmented data, which slows down pricing and competitor response.

# 3. Scope Definition

## 3.1 In-Scope

- Web-based data entry: market visit reports, interviews, structured surveys.

- Competitor pricing capture and comparison.

- D365FO integration for customer, product, and sales data.

- CUAS integration for login and role-based access (no separate access system built).

- CNS integration for email, SMS, and WhatsApp notifications.

- Power BI dashboards with basic scheduled reports.

## 3.2 Out-of-Scope (This Release)

- React Native mobile app (Future Phase).

- Offline data collection (Future Phase).

- Photo/video capture (Future Phase).

- GPS/location tracking (Future Phase).

- Barcode/QR scanning (Future Phase).

- Full CRM replacement of D365FO.

- Automated pricing-recommendation engine.

- Custom report builder beyond standard Power BI reports.

- Push notifications and in-app notifications (CNS covers email, SMS, WhatsApp only).

## 3.3 Assumptions

- D365FO, CUAS, and CNS all expose APIs the in-house team can integrate with.

- Marketing and field staff have web browser access to use the portal.

## 3.4 Constraints

- The 6-week timeline is fixed, so scope is limited to what the team can deliver in that time.

## 3.5 Phase 0 Deliverables

| Deliverable | Description |
| --- | --- |
| Project Charter | Objectives and success criteria (Section 1) |
| Business Case | Justification and expected benefits (Section 2) |
| Scope Definition | In/out of scope, assumptions, constraints (Section 3) |
| Stakeholder Identification | Stakeholder list and engagement approach (Section 4) |
| Team Formation | Roles and responsibilities (Section 5) |
| Product Backlog | Initial epics and user stories (Section 6) |
| Sprint Planning | Sprint 0 plan (Section 7) |
| Project Plan | 6-week delivery approach (Section 8) |
| Sprint Roadmap | Sprint-by-sprint plan (Section 9) |
| Risk Register | Key risks and mitigation (Section 10) |
| Communication Plan | Who gets updated, how, and when (Section 11) |
| Project Schedule | Week-by-week milestones (Section 12) |

# 4. Stakeholder Identification

| Stakeholder | Role | Interest | Engagement |
| --- | --- | --- | --- |
| Tsegaye Nigusie | Marketing Intelligence Officer — main requester | Defines requirements, approves features | Weekly check-ins, UAT sign-off |
| Marketing Dept. Management | Sponsor | Budget and strategic alignment | Milestone reviews |
| Chief Technology Officer (CTO) | Executive Sponsor & Technical governance | Strategic oversight, technology alignment, final project approval | Executive milestone reviews and key decision meetings |
| IT Department Head | Delivery oversight | Resourcing, technical approval | Bi-weekly status updates |
| In-house Dev Team | Delivery team | Builds and delivers the system | Daily stand-ups, sprint reviews |
| Field Marketing/Sales Staff | End users | Ease of use, portal reliability | Training and UAT |
| D365FO / CUAS / CNS Owners | Internal systems owners | API access, data integrity, uptime | Joint integration planning in Week 1 |

# 5. Team Formation

## 5.1 Project Team

| Role | Responsibility | Assigned To |
| --- | --- | --- |
| Project Manager | Planning, tracking, stakeholder communication | Mr. Estifanos Alemseged |
| Backend Developer (Node.js/Express) | API development, business logic, D365FO integration; MS SQL Server schema design, performance, and backups | Mr. Woluman Urgesa |
| Frontend Developer (Next.js) | Web admin portal, report builder UI; Power BI dashboard design, KPI modeling, report automation | Mr. Woluman Urgesa |
| QA / Test Engineer | Test planning, functional testing, UAT support | Mr. Hirko Gemechu |

## 5.2 Reporting Structure

The Project Manager reports to the IT Department Head and the Marketing Department sponsor. Team members report to the Project Manager for the duration of the project.

# 6. Product Backlog Creation

## 6.1 Epics

| Epic ID | Epic | Priority |
| --- | --- | --- |
| EPIC-01 | Survey & Questionnaire Builder | High |
| EPIC-02 | Competitor & Pricing Module | High |
| EPIC-03 | D365FO Integration (customer, sales, product data) | High |
| EPIC-04 | CUAS Integration (login & role-based access) | High |
| EPIC-05 | CNS Integration (email, SMS, WhatsApp notifications) | Medium |
| EPIC-06 | Power BI Dashboards & Basic Reports | High |

## 6.2 Sample User Stories

- As a marketing officer, I can log a market visit report through the web portal.

- As a user, I can log in using my normal company account through CUAS.

- As a marketing manager, I get a WhatsApp or email alert (via CNS) when a new report is submitted.

- As a marketing analyst, I can compare our pricing to competitor pricing on a dashboard.

## 6.3 Backlog Grooming

The backlog is reviewed at the end of each sprint, with the Marketing Intelligence Officer involved in prioritization.

# 7. Sprint Planning — Sprint 0

## 7.1 Objective

Sprint 0 sets up the technical foundation before feature development starts. It runs for Week 1 of the 6-week schedule.

## 7.2 Key Activities

- Confirm architecture: Node.js/Express API, Next.js portal, MS SQL Server database.

- Set up development and staging environments and source control.

- Confirm API access for D365FO, CUAS, and CNS.

- Set up the Power BI workspace.

- Groom and estimate the backlog (Section 6).

## 7.3 Exit Criteria

- Environments are ready for all team members.

- D365FO, CUAS, and CNS access is confirmed.

- Backlog is estimated and ready for Sprint 1.

# 8. Project Plan

## 8.1 Delivery Approach

The project is delivered in one continuous 6-week schedule of six weekly sprints, so the Marketing Department can see progress regularly. Each sprint runs Monday through Saturday, with Sundays off.

## 8.2 Phase Overview (6 Weeks)

| Phase | Objective | Timing |
| --- | --- | --- |
| Sprint 1 | Setup & Architecture: architecture, environments, access to D365FO/CUAS/CNS, Power BI workspace, backlog ready | Week 1 |
| Sprint 2 | Core Build: web admin portal foundation, data model, CUAS login integration | Week 2 |
| Sprint 3 | Survey builder and competitor pricing module | Week 3 |
| Sprint 4 | D365FO sync and CNS notifications (email, SMS, WhatsApp) | Week 4 |
| Sprint 5 | Power BI dashboards and reports | Week 5 |
| Sprint 6 | UAT, fixes, training, deployment | Week 6 |

# 9. Sprint Roadmap

| Sprint | Timing | Focus |
| --- | --- | --- |
| Sprint 1 | Week 1 | Setup & Architecture: architecture, environments, access to D365FO/CUAS/CNS, Power BI workspace, backlog ready |
| Sprint 2 | Week 2 | Core Build: web admin portal foundation, data model, CUAS login integration |
| Sprint 3 | Week 3 | Survey builder and competitor pricing module |
| Sprint 4 | Week 4 | D365FO sync and CNS notifications (email, SMS, WhatsApp) |
| Sprint 5 | Week 5 | Power BI dashboards and reports |
| Sprint 6 | Week 6 | UAT, fixes, training, deployment |

# 10. Risk Register / Risk Assessment

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Team members are pulled onto other IT work during the 6 weeks | High | High | Confirm dedicated allocation before kickoff | IT Dept. Head |
| R-02 | D365FO, CUAS, or CNS API access is delayed or limited | Medium | High | Confirm access in Week 1 before development starts | Backend Developer |
| R-03 | Extra feature requests stretch the 6-week scope | Medium | Medium | Keep scope fixed per Section 3; log extra requests for a later phase | Project Manager |
| R-04 | Low field staff adoption after go-live | Medium | Medium | Involve users in UAT; short training before go-live | Marketing Sponsor |
| R-05 | Data entered in the portal is incomplete or inconsistent | Medium | Medium | Validation rules and required fields in the portal | QA Engineer |

# 11. Communication Plan

| Audience | Frequency | Channel | Content |
| --- | --- | --- | --- |
| Sponsors / Steering | End of each phase | Meeting + short summary | Progress, risks, decisions |
| Marketing Intelligence Officer | Weekly | Meeting / email | Requirement checks, feature reviews |
| Development Team | Daily | Stand-up | Progress and blockers |
| Marketing Department | End of each sprint | Sprint review demo | Working features, feedback |
| Field Staff | Week 6 | Training session | Onboarding before go-live |
| IT Department Head | Bi-weekly | Status update | Resourcing and risks |

# 12. Project Schedule

Assumes a project start of Monday, 27 July 2026, pending Charter approval. Each sprint runs Monday through Saturday, with Sundays off.

| Milestone | Target Date |
| --- | --- |
| Charter Approved / Kickoff | 27 July 2026 |
| Sprint 1 Complete — Setup & Architecture | 27 Jul – 1 Aug 2026 |
| Sprint 2 Complete — Core Build | 3 Aug – 8 Aug 2026 |
| Sprint 3 Complete — Survey Builder & Pricing Module | 10 Aug – 15 Aug 2026 |
| Sprint 4 Complete — D365FO Sync & CNS Notifications | 17 Aug – 22 Aug 2026 |
| Sprint 5 Complete — Power BI Dashboards | 24 Aug – 29 Aug 2026 |
| Sprint 6 — UAT, Training & Go-Live | 31 Aug – 5 Sep 2026 |