KERCHANSHE GROUP

Marketing Department

Hybrid Market Intelligence System (MIS)

Phase 0 — Project Planning Package

Project Code: KG-MIS-2026-DEV-PROPOSAL

| Field | Detail |
| --- | --- |
| Project Sponsor | Marketing Department, Kerchanshe Group |
| Requesting Officer | Tsegaye Nigusie — Marketing Intelligence Officer |
| Delivery Owner | IT Department (In-house Development Team) |
| Project Manager | TBD |
| Document Status | Draft v1.0 — For Review |
| Prepared Date | July 2026 |

# Table of Contents

Table of Contents	2

1. Project Charter	4

1.1 Purpose	4

1.2 Business Justification	4

1.3 Project Objectives	4

1.4 High-Level Scope	4

1.5 Success Criteria	4

1.6 High-Level Timeline & Budget (Indicative)	4

1.7 Authorization	5

2. Business Case	6

2.1 Problem Statement	6

2.2 Proposed Solution	6

2.3 Alternatives Considered	6

2.4 Expected Benefits	6

2.5 Indicative Cost-Benefit Overview	6

2.6 Risk of Not Proceeding	7

3. Scope Definition	8

3.1 In-Scope Features	8

3.2 Out-of-Scope (This Phase)	8

3.3 Assumptions	8

3.4 Constraints	8

3.5 Phase 0 Deliverables	8

4. Stakeholder Identification	10

5. Team Formation	11

5.1 Proposed Project Team	11

5.2 Reporting Structure	11

5.3 Resourcing Notes	11

6. Product Backlog Creation	12

6.1 Epics	12

6.2 Sample Initial User Stories	12

6.3 Backlog Grooming Cadence	12

7. Sprint Planning — Sprint 0	13

7.1 Sprint 0 Objective	13

7.2 Sprint 0 Duration	13

7.3 Key Activities	13

7.4 Sprint 0 Exit Criteria	13

8. Project Plan	14

8.1 Delivery Methodology	14

8.2 Phase Overview	14

8.3 Governance	14

9. Sprint Roadmap	15

10. Risk Register / Risk Assessment	16

11. Communication Plan	17

12. Project Schedule	18

# 1. Project Charter

## 1.1 Purpose

This charter formally authorizes the Hybrid Market Intelligence System (MIS) project and grants the Project Manager authority to apply organizational resources to project activities. It confirms the shift from the originally proposed external stack (Flutter, React.js, .NET Core, SQL Server) to an in-house delivery stack (Node.js, Next.js, Express, PostgreSQL, TypeScript, React Native), while retaining Power BI for analytics and Dynamics 365 Finance & Operations (D365FO) integration for ERP/CRM data.

## 1.2 Business Justification

The Marketing Department currently lacks a centralized system to capture competitor pricing intelligence, distributor feedback, survey data, and field observations. Data is fragmented across manual reports, spreadsheets, and ad-hoc communications, delaying decision-making on pricing, promotions, and distribution. The MIS will consolidate these data streams into a single platform with automated analytics and reporting, integrated with existing D365FO and Power BI investments.

## 1.3 Project Objectives

- Deliver a centralized platform for field data collection, competitor pricing intelligence, and distributor feedback.

- Provide survey and questionnaire management with offline capability for field staff.

- Deliver real-time, drill-down analytics and automated reporting through Power BI.

- Integrate securely with D365FO for customer, sales, and product master data.

- Establish a maintainable, in-house-owned technology stack to reduce long-term vendor dependency.

## 1.4 High-Level Scope

In scope: mobile field data capture app, web-based administration and reporting portal, survey/questionnaire builder, multimedia (photo/video) capture and tagging, competitor and pricing intelligence module, D365FO integration layer, Power BI dashboards, role-based access control.

Out of scope (Phase 0-1): full CRM replacement, automated pricing-decision engine beyond basic recommendation prompts, integrations with systems other than D365FO unless separately approved.

## 1.5 Success Criteria

- System live in production with field teams actively submitting data within the approved timeline.

- Power BI dashboards reflect field and D365FO data with data latency under an agreed threshold (target: near real-time to daily sync, to be confirmed in SRD).

- User acceptance sign-off from Marketing Department stakeholders.

- Project delivered within approved budget and schedule tolerances.

## 1.6 High-Level Timeline & Budget (Indicative)

| Item | Estimate | Notes |
| --- | --- | --- |
| Target Start Date | July 2026 | Pending charter approval |
| Estimated Duration | 6–9 months | To be refined in Project Plan (Section 8) |
| Budget | TBD | In-house delivery — primarily internal labor cost; infrastructure/licensing costs to be estimated |

## 1.7 Authorization

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | TBD |  |  |
| Project Owner | MTK dept. |  |  |
| Chief Technology Officer (CTO) | Mr. Melkamu Alamerew |  |  |
| IT Department Head | TBD |  |  |
| Project Manager | TBD |  |  |
| Development Team | TBD |  |  |

# 2. Business Case

## 2.1 Problem Statement

Market intelligence today is collected manually and inconsistently across regions and business units. Competitor pricing, distributor feedback, and field survey data are not standardized, are slow to consolidate, and are disconnected from D365FO and Power BI, limiting management's ability to make timely, data-driven pricing and marketing decisions.

## 2.2 Proposed Solution

A hybrid Market Intelligence System combining a mobile app for field data collection, a web application for administration and workflow, a centralized SQL-based data store, D365FO integration, and Power BI for analytics and dashboards — delivered using the in-house team's existing skill set (Node.js, Next.js, Express, PostgreSQL, TypeScript, React Native).

## 2.3 Alternatives Considered

| Option | Description | Assessment |
| --- | --- | --- |
| A. Original proposed stack | Flutter, React.js, .NET Core, SQL Server via external vendor/contractors | Higher cost, external dependency, longer onboarding; rejected |
| B. In-house stack (recommended) | Node.js, Next.js, Express, PostgreSQL, TypeScript, React Native | Leverages existing team skills, lower cost, faster iteration, easier long-term maintenance |
| C. Buy off-the-shelf MIS/CRM add-on | Purchase a commercial market intelligence module | Limited fit to Kerchanshe-specific workflows and D365FO integration; higher licensing cost; not pursued further |

## 2.4 Expected Benefits

- Data-driven decision-making across all business units.

- Faster and more accurate reporting via automated dashboards and scheduled reports.

- Improved pricing, product, and marketing strategies through competitor benchmarking.

- Stronger visibility into customer needs and competitor actions.

- A standardized, efficient market intelligence process replacing manual consolidation.

## 2.5 Indicative Cost-Benefit Overview

| Category | Estimate / Notes |
| --- | --- |
| Internal development effort | TBD — to be sized once backlog (Section 6) is estimated |
| Infrastructure (DB hosting, servers) | TBD — depends on on-prem vs cloud decision |
| Power BI / D365FO licensing | Existing licenses assumed reusable; confirm with IT procurement |
| Avoided cost | Reduced manual reporting effort; avoided external vendor/contractor fees |
| Payback consideration | To be modeled once effort and infrastructure estimates are finalized |

## 2.6 Risk of Not Proceeding

Without the MIS, the Marketing Department continues to rely on fragmented, manual data collection, resulting in delayed competitor response, inconsistent pricing decisions, and limited ability to benchmark performance across regions.

# 3. Scope Definition

## 3.1 In-Scope Features

- Field data collection: market visit reports, customer/distributor interviews, structured surveys.

- Photo/video capture with metadata, linked to surveys and reports.

- Sales and competitor pricing data capture and comparison.

- D365FO integration for customer, product, and sales master data.

- Power BI dashboards: KPI tracking, drill-down (country → region → city → outlet), competitor benchmarking.

- Automated report generation (Daily/Weekly/Monthly) with PDF/Excel/PowerPoint-ready export.

- Custom report builder with filters by product, region, time, and business unit.

- Survey builder with logic flow and offline capability.

- Role-based access control and security.

## 3.2 Out-of-Scope (This Phase)

- Full CRM replacement or migration away from D365FO.

- Advanced AI-driven pricing recommendation engine (basic rule-based suggestions only).

- Integrations with systems beyond D365FO, unless separately requested and approved.

- Audio transcription automation beyond basic recording capture (flagged as a future enhancement).

## 3.3 Assumptions

- Existing D365FO and Power BI licenses can be extended to this system without material additional licensing cost.

- The in-house team has or can be given the necessary D365FO API/integration access.

- Field staff have access to smartphones/tablets capable of running the React Native app, including offline data capture.

## 3.4 Constraints

- Delivery relies on internal IT department capacity alongside other ongoing IT commitments.

- Network connectivity in field locations may be intermittent, requiring robust offline-sync design.

## 3.5 Phase 0 Deliverables

| Deliverable | Description |
| --- | --- |
| Project Charter | Formal authorization, objectives, and success criteria (Section 1) |
| Business Case | Justification, alternatives, and expected benefits (Section 2) |
| Scope Definition | In/out of scope, assumptions, constraints (Section 3) |
| Stakeholder Identification | Stakeholder register and engagement approach (Section 4) |
| Team Formation | Roles, responsibilities, reporting lines (Section 5) |
| Product Backlog Creation | Initial epics and prioritized backlog (Section 6) |
| Sprint Planning | Sprint 0 plan and cadence (Section 7) |
| Project Plan | Phased delivery approach and methodology (Section 8) |
| Sprint Roadmap | Release-level roadmap across sprints (Section 9) |
| Risk Register / Risk Assessment | Identified risks, likelihood, impact, mitigation (Section 10) |
| Communication Plan | Stakeholder communication cadence and channels (Section 11) |
| Project Schedule | Milestone-level schedule (Section 12) |

# 4. Stakeholder Identification

Stakeholders below are identified from the project request and typical delivery structure. Names marked TBD should be confirmed during project kickoff.

| Stakeholder | Role / Department | Interest | Influence | Engagement Approach |
| --- | --- | --- | --- | --- |
| Tsegaye Nigusie | Marketing Intelligence Officer, Marketing Dept. | Primary requester; defines business requirements | High | Weekly check-ins; requirement validation; UAT sign-off |
| Marketing Department Management | Sponsor / Business Owner | Budget approval, strategic alignment | High | Steering committee updates; milestone reviews |
| IT Department Head | Delivery oversight | Resource allocation, technical governance | High | Bi-weekly status reporting |
| In-house Development Team | Delivery team (PM, developers, QA) | Execution of build and delivery | High | Daily stand-ups; sprint ceremonies |
| Field Marketing / Sales Staff | End users (mobile app) | Usability, offline reliability | Medium | UAT participation; training sessions |
| D365FO/ERP System Owner | Integration counterpart | Data integrity, API access, security | Medium | Integration design workshops |
| Power BI / BI Team | Analytics and dashboard support | Dashboard design, data model alignment | Medium | Joint dashboard design sessions |
| Distributors / External Respondents | Data subjects (indirect) | Ease of survey participation | Low | Communicated via field staff, not directly engaged |

# 5. Team Formation

## 5.1 Proposed Project Team

| Role | Responsibility | Assigned To |
| --- | --- | --- |
| Project Manager | Overall planning, tracking, stakeholder communication | TBD |
| Backend Developer (Node.js/Express) | API development, business logic, D365FO integration layer | TBD |
| Frontend Developer (Next.js) | Web administration portal, report builder UI | TBD |
| Mobile Developer (React Native) | Field data collection app, offline sync | TBD |
| Database Administrator | PostgreSQL schema design, performance, backups | TBD |
| BI / Power BI Analyst | Dashboard design, KPI modeling, report automation | TBD |
| QA / Test Engineer | Test planning, functional and UAT support | TBD |
| D365FO Integration Specialist | ERP-side configuration and data mapping | TBD |

## 5.2 Reporting Structure

The Project Manager reports to the IT Department Head and the Marketing Department sponsor on a dual-reporting basis for this project. Development team members report functionally to the Project Manager for the duration of the project while retaining administrative reporting to their respective IT team leads.

## 5.3 Resourcing Notes

- Team composition above is indicative; actual staffing depends on concurrent IT department commitments.

- Where dedicated specialists are unavailable in-house, the PM should flag shared/part-time allocation risk in the Risk Register (Section 10).

# 6. Product Backlog Creation

## 6.1 Epics

The initial backlog is organized into epics derived directly from the system requirements. Detailed user stories will be elaborated during backlog refinement in Sprint 0 and beyond.

| Epic ID | Epic | Priority |
| --- | --- | --- |
| EPIC-01 | Field Data Collection App (React Native, offline capture) | High |
| EPIC-02 | Survey & Questionnaire Builder | High |
| EPIC-03 | Multimedia Capture & Tagging (photo/video + metadata) | Medium |
| EPIC-04 | Competitor & Pricing Intelligence Module | High |
| EPIC-05 | D365FO Integration Layer | High |
| EPIC-06 | Centralized Data Store & Validation (PostgreSQL) | High |
| EPIC-07 | Power BI Dashboards & KPI Tracking | High |
| EPIC-08 | Automated & Custom Report Builder | Medium |
| EPIC-09 | Role-Based Access Control & Security | High |
| EPIC-10 | Alerts & Basic Recommendation Engine | Low |

## 6.2 Sample Initial User Stories

- As a field officer, I can log a market visit report offline and have it sync automatically when connectivity is available.

- As a marketing analyst, I can compare our pricing against competitor pricing by region on a dashboard.

- As a marketing manager, I can receive a scheduled weekly PDF report summarizing distributor feedback.

- As a system admin, I can assign role-based permissions to control access to sensitive pricing data.

- As a field officer, I can attach photos of shelf displays to a specific survey response.

## 6.3 Backlog Grooming Cadence

The backlog will be reviewed and refined at the end of each sprint, with the Marketing Intelligence Officer participating in prioritization to ensure alignment with business needs.

# 7. Sprint Planning — Sprint 0

## 7.1 Sprint 0 Objective

Sprint 0 focuses on environment setup, architecture finalization, and backlog readiness rather than shippable features, establishing the technical foundation for subsequent development sprints.

## 7.2 Sprint 0 Duration

2 weeks (indicative), immediately following Project Charter approval.

## 7.3 Key Activities

- Finalize technical architecture (Node.js/Express API, Next.js portal, React Native app, PostgreSQL schema).

- Set up source control, CI/CD pipeline, and development/staging environments.

- Confirm D365FO integration approach and obtain necessary API access/credentials.

- Set up Power BI workspace and initial data model skeleton.

- Groom and estimate the top of the product backlog (Section 6).

- Define Definition of Ready and Definition of Done for user stories.

- Establish sprint ceremonies cadence (planning, daily stand-up, review, retrospective).

## 7.4 Sprint 0 Exit Criteria

- Development environments operational for all team members.

- Architecture and data model reviewed and approved by the Project Manager and technical lead.

- Prioritized, estimated backlog ready for Sprint 1 planning.

# 8. Project Plan

## 8.1 Delivery Methodology

The project will be delivered using an Agile/Scrum approach with two-week sprints, following the Sprint 0 foundation phase. This suits the evolving nature of requirements across multiple business units and allows the Marketing Department to review working increments regularly.

## 8.2 Phase Overview

| Phase | Objective | Indicative Duration |
| --- | --- | --- |
| 0. Project Planning | Define scope, resources, timeline, and roadmap | 2–3 weeks |
| 1. Foundation (Sprint 0) | Environment setup, architecture, backlog readiness | 2 weeks |
| 2. Core Development | Build field app, web portal, D365FO integration, data store | 12–16 weeks (multiple sprints) |
| 3. Analytics & Reporting | Power BI dashboards, automated reporting, custom report builder | 4–6 weeks |
| 4. Testing & UAT | System testing, integration testing, user acceptance testing | 3–4 weeks |
| 5. Deployment & Rollout | Production deployment, field staff training, go-live | 2–3 weeks |
| 6. Closure & Handover | Documentation, lessons learned, support handover | 1–2 weeks |

## 8.3 Governance

- Steering committee review at the end of each phase.

- Sprint review at the end of every sprint with Marketing Department representation.

- Change requests routed through the Project Manager and logged against the Risk Register / Scope Definition.

# 9. Sprint Roadmap

Indicative roadmap; sprint numbers and content will be refined after backlog estimation in Sprint 0.

| Sprint | Focus | Target Output |
| --- | --- | --- |
| Sprint 0 | Foundation & setup | Environments, architecture, groomed backlog |
| Sprint 1–2 | Core data model & auth | PostgreSQL schema, RBAC, base API |
| Sprint 3–4 | Field data collection app | React Native app with offline capture (MVP) |
| Sprint 5–6 | Survey builder & multimedia | Survey logic flow, photo/video tagging |
| Sprint 7–8 | D365FO integration | Customer/product/sales data sync |
| Sprint 9–10 | Competitor & pricing module | Pricing comparison and benchmarking features |
| Sprint 11–12 | Power BI dashboards | KPI dashboards, drill-down views |
| Sprint 13 | Automated reporting | Scheduled report generation and export |
| Sprint 14 | UAT & hardening | Bug fixes, performance tuning, UAT feedback |
| Sprint 15 | Deployment & training | Go-live, field staff onboarding |

# 10. Risk Register / Risk Assessment

| ID | Risk | Category | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | In-house team capacity constrained by other IT commitments | Resourcing | High | High | Secure dedicated allocation in Project Charter; escalate conflicts early | IT Dept. Head |
| R-02 | D365FO integration access/API limitations discovered late | Technical | Medium | High | Validate API access and data model in Sprint 0 | Backend Lead |
| R-03 | Intermittent field connectivity affects offline sync reliability | Technical | Medium | Medium | Design robust offline-first sync with conflict resolution; field pilot testing | Mobile Lead |
| R-04 | Scope creep from additional business unit requests | Scope | Medium | Medium | Formal change request process; scope sign-off in Section 3 | Project Manager |
| R-05 | Power BI/D365FO licensing gaps for new use cases | Financial | Low | Medium | Confirm licensing terms with IT procurement in Sprint 0 | IT Dept. Head |
| R-06 | Low field staff adoption due to change resistance | Organizational | Medium | Medium | Early UAT involvement; structured training and rollout plan | Marketing Sponsor |
| R-07 | Data quality issues from manual field entry | Data | Medium | Medium | Validation rules, mandatory fields, automated data cleaning (per SRD) | QA Lead |
| R-08 | Key technical resource unavailability (single point of failure) | Resourcing | Low | High | Cross-train team members; document architecture decisions | Project Manager |

# 11. Communication Plan

| Audience | Frequency | Channel | Content | Owner |
| --- | --- | --- | --- | --- |
| Steering Committee / Sponsors | Monthly / End of phase | Meeting + summary report | Phase progress, budget, key risks/decisions | Project Manager |
| Marketing Intelligence Officer | Weekly | Meeting / email | Requirement clarifications, review of increments | Project Manager |
| Development Team | Daily | Stand-up meeting | Progress, blockers, task coordination | Project Manager / Scrum lead |
| Marketing Department (broader) | End of each sprint / phase | Sprint review demo | Working software demonstration, feedback | Project Manager |
| Field Staff (end users) | Prior to rollout, then as needed | Training sessions, email | Training, onboarding, change notices | Marketing Sponsor / PM |
| IT Department Head | Bi-weekly | Status report | Resourcing, technical risks, escalations | Project Manager |

# 12. Project Schedule

Milestone dates below assume a target project start of July 2026, pending Project Charter approval. Dates will be finalized once resourcing (Section 5) and backlog estimation (Section 6) are complete.

| Milestone | Target Date (Indicative) |
| --- | --- |
| Project Charter Approved | Mid-July 2026 |
| Sprint 0 Complete (Foundation) | Late-July 2026 |
| Core Development Complete | Q4 2026 |
| Analytics & Reporting Complete | Q4 2026 – Q1 2027 |
| UAT Complete | Q1 2027 |
| Go-Live / Deployment | Q1 2027 |
| Project Closure & Handover | Q1 2027 |

Note: These are placeholder, planning-level dates for the initial proposal package. They should be revisited and confirmed with the assigned Project Manager and resourcing plan before formal baselining.