KERCHANSHE GROUP

Marketing Department

Hybrid Market Intelligence System (MIS)

Phase 0 — Project Planning Package

Project Code: KG-MIS-2026-DEV-PROPOSAL

| Field | Detail |
| --- | --- |
| Project Sponsor | Marketing Department, Kerchanshe Group |
| Requesting Officer | Tsegaye Nigusie — Marketing Intelligence Officer |
| Delivery Owner | IT Department (In-house Development Team) |
| Project Manager | TBD |
| Document Status | Draft v1.1 — For Review |
| Prepared Date | July 2026 |

# Table of Contents

# 1. Project Charter

## 1.1 Purpose

This charter authorizes the Hybrid Market Intelligence System (MIS) project. It confirms delivery using the in-house team's existing skills (Node.js, Next.js, Express, PostgreSQL, TypeScript, React Native), with Power BI for analytics and integration with three internal systems: D365FO (ERP/CRM data), CUAS (role-based access), and CNS (notifications).

## 1.2 Business Justification

Market data — competitor pricing, distributor feedback, and field surveys — is currently collected manually and is hard to consolidate. The MIS will bring this data into one system, connected to the tools the business already uses, so Marketing can act on it faster.

## 1.3 Project Objectives

- Give field teams one app to collect market visit reports, surveys, and photos/videos — including offline.

- Capture and compare competitor pricing against our own.

- Provide Power BI dashboards and simple automated reports.

- Connect to D365FO for customer, sales, and product data.

- Use CUAS for user login and role-based access instead of building this from scratch.

- Use CNS for notifications (email, SMS, WhatsApp).

## 1.4 High-Level Scope

In scope: mobile field data app, web admin portal, survey builder, photo/video capture, competitor pricing module, Power BI dashboards, and integration with D365FO, CUAS, and CNS.

Out of scope for this release: a full CRM replacement, an automated pricing-decision engine, a custom report builder beyond Power BI, and any notification channel other than email, SMS, and WhatsApp (no push or in-app notifications).

## 1.5 Success Criteria

- System is live and field teams are submitting data.

- Power BI dashboards show field and D365FO data correctly.

- Login/access works through CUAS and notifications work through CNS.

- Marketing Department signs off after user acceptance testing.

## 1.6 Timeline & Budget (Indicative)

| Item | Estimate | Notes |
| --- | --- | --- |
| Target Start Date | 6 July 2026 | Pending charter approval |
| Duration | 8 weeks | See Project Plan, Section 8 |
| Budget | TBD | Mainly internal labor; confirm any CUAS/CNS/D365FO usage costs with IT |

## 1.7 Authorization

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | TBD |  |  |
| Marketing Dept. Representative | Tsegaye Nigusie |  |  |
| IT Department Head | TBD |  |  |
| Project Manager | TBD |  |  |

# 2. Business Case

## 2.1 Problem Statement

Competitor pricing, distributor feedback, and field survey data are collected manually today. This is slow, inconsistent, and disconnected from D365FO and Power BI, which delays pricing and marketing decisions.

## 2.2 Proposed Solution

A single system for field data collection, competitor pricing, surveys, and reporting — built in-house, connected to D365FO for master data, CUAS for access control, and CNS for notifications.

## 2.3 Expected Benefits

- Faster, more consistent market intelligence reporting.

- Better pricing and marketing decisions from competitor benchmarking.

- One login and access system (CUAS) instead of a separate one for this app.

- Automatic notifications (CNS) instead of manual follow-ups.

- Lower cost and faster delivery by using the in-house team and existing internal systems.

## 2.4 Indicative Cost-Benefit Overview

| Category | Estimate / Notes |
| --- | --- |
| Internal development effort | TBD — sized once the backlog (Section 6) is estimated |
| Infrastructure (hosting, database) | TBD — depends on on-prem vs. cloud decision |
| Power BI / D365FO / CUAS / CNS | Assumed existing internal systems; confirm any usage limits with IT |
| Avoided cost | Less manual reporting effort; no external vendor fees |

## 2.5 Risk of Not Proceeding

Without the MIS, Marketing continues to rely on manual, fragmented data, which slows down pricing and competitor response.

# 3. Scope Definition

## 3.1 In-Scope

- Field data collection: market visit reports, interviews, structured surveys.

- Photo/video capture, linked to surveys and reports.

- Competitor pricing capture and comparison.

- D365FO integration for customer, product, and sales data.

- CUAS integration for login and role-based access (no separate access system built).

- CNS integration for email, SMS, and WhatsApp notifications.

- Power BI dashboards with basic scheduled reports.

## 3.2 Out-of-Scope (This Release)

- Full CRM replacement of D365FO.

- Automated pricing-recommendation engine.

- Custom report builder beyond standard Power BI reports.

- Push notifications and in-app notifications (CNS covers email, SMS, WhatsApp only).

## 3.3 Assumptions

- D365FO, CUAS, and CNS all expose APIs the in-house team can integrate with.

- Field staff have smartphones/tablets that can run the mobile app, including offline use.

## 3.4 Constraints

- The 8-week timeline is fixed, so scope is limited to what the team can deliver in that time.

- Field network connectivity may be unreliable, so the app needs offline support.

## 3.5 Phase 0 Deliverables

| Deliverable | Description |
| --- | --- |
| Project Charter | Objectives and success criteria (Section 1) |
| Business Case | Justification and expected benefits (Section 2) |
| Scope Definition | In/out of scope, assumptions, constraints (Section 3) |
| Stakeholder Identification | Stakeholder list and engagement approach (Section 4) |
| Team Formation | Roles and responsibilities (Section 5) |
| Product Backlog | Initial epics and user stories (Section 6) |
| Sprint Planning | Sprint 0 plan (Section 7) |
| Project Plan | 8-week delivery approach (Section 8) |
| Sprint Roadmap | Sprint-by-sprint plan (Section 9) |
| Risk Register | Key risks and mitigation (Section 10) |
| Communication Plan | Who gets updated, how, and when (Section 11) |
| Project Schedule | Week-by-week milestones (Section 12) |

# 4. Stakeholder Identification

Names marked TBD should be confirmed at project kickoff.

| Stakeholder | Role | Interest | Engagement |
| --- | --- | --- | --- |
| Tsegaye Nigusie | Marketing Intelligence Officer — main requester | Defines requirements, approves features | Weekly check-ins, UAT sign-off |
| Marketing Dept. Management | Sponsor | Budget and strategic alignment | Milestone reviews |
| IT Department Head | Delivery oversight | Resourcing, technical approval | Bi-weekly status updates |
| In-house Dev Team | Delivery team | Builds and delivers the system | Daily stand-ups, sprint reviews |
| Field Marketing/Sales Staff | End users | Ease of use, offline reliability | Training and UAT |
| D365FO / CUAS / CNS Owners | Internal systems owners | API access, data integrity, uptime | Joint integration planning in Week 1 |

# 5. Team Formation

## 5.1 Project Team

| Role | Responsibility | Assigned To |
| --- | --- | --- |
| Project Manager | Planning, tracking, stakeholder communication | TBD |
| Backend Developer (Node.js/Express) | API development, business logic, D365FO integration; PostgreSQL schema design, performance, and backups | TBD |
| Frontend Developer (Next.js) | Web admin portal, report builder UI; Power BI dashboard design, KPI modeling, report automation | TBD |
| Mobile Developer (React Native) | Field data collection app, offline sync | TBD |
| QA / Test Engineer | Test planning, functional testing, UAT support | TBD |

A separate database administrator and Power BI analyst are not required — these responsibilities are covered by the Backend and Frontend Developers above.

## 5.2 Reporting Structure

The Project Manager reports to the IT Department Head and the Marketing Department sponsor. Team members report to the Project Manager for the duration of the project.

# 6. Product Backlog Creation

## 6.1 Epics

| Epic ID | Epic | Priority |
| --- | --- | --- |
| EPIC-01 | Field Data Collection App (offline capture) | High |
| EPIC-02 | Survey & Questionnaire Builder | High |
| EPIC-03 | Photo/Video Capture & Tagging | Medium |
| EPIC-04 | Competitor & Pricing Module | High |
| EPIC-05 | D365FO Integration (customer, sales, product data) | High |
| EPIC-06 | CUAS Integration (login & role-based access) | High |
| EPIC-07 | CNS Integration (email, SMS, WhatsApp notifications) | Medium |
| EPIC-08 | Power BI Dashboards & Basic Reports | High |

## 6.2 Sample User Stories

- As a field officer, I can log a market visit report offline and it syncs when I'm back online.

- As a user, I can log in using my normal company account through CUAS.

- As a marketing manager, I get a WhatsApp or email alert (via CNS) when a new report is submitted.

- As a marketing analyst, I can compare our pricing to competitor pricing on a dashboard.

- As a field officer, I can attach photos to a survey response.

## 6.3 Backlog Grooming

The backlog is reviewed at the end of each sprint, with the Marketing Intelligence Officer involved in prioritization.

# 7. Sprint Planning — Sprint 0

## 7.1 Objective

Sprint 0 sets up the technical foundation before feature development starts. It runs for Week 1 of the 8-week schedule.

## 7.2 Key Activities

- Confirm architecture: Node.js/Express API, Next.js portal, React Native app, PostgreSQL database.

- Set up development and staging environments and source control.

- Confirm API access for D365FO, CUAS, and CNS.

- Set up the Power BI workspace.

- Groom and estimate the backlog (Section 6).

## 7.3 Exit Criteria

- Environments are ready for all team members.

- D365FO, CUAS, and CNS access is confirmed.

- Backlog is estimated and ready for Sprint 1.

# 8. Project Plan

## 8.1 Delivery Approach

The project is delivered in one continuous 8-week schedule using short, focused sprints, so the Marketing Department can see progress regularly.

## 8.2 Phase Overview (8 Weeks)

| Phase | Objective | Timing |
| --- | --- | --- |
| 0. Planning & Setup | Architecture, environments, access to D365FO/CUAS/CNS, backlog ready | Week 1 |
| 1. Core Build | Field app, data model, CUAS login integration | Weeks 2–3 |
| 2. Feature Build | Survey builder, photo/video capture, CNS notifications, D365FO sync | Weeks 4–5 |
| 3. Analytics | Competitor pricing module, Power BI dashboards and reports | Weeks 6–7 |
| 4. Testing & Go-Live | UAT, fixes, training, deployment | Week 8 |

# 9. Sprint Roadmap

| Sprint | Timing | Focus |
| --- | --- | --- |
| Sprint 0 | Week 1 | Setup, architecture, access confirmation, backlog |
| Sprint 1 | Weeks 2–3 | Field data app, data model, CUAS login |
| Sprint 2 | Weeks 4–5 | Survey builder, photo/video capture, CNS notifications, D365FO sync |
| Sprint 3 | Weeks 6–7 | Competitor pricing module, Power BI dashboards |
| Final Week | Week 8 | UAT, fixes, training, go-live |

# 10. Risk Register / Risk Assessment

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Team members are pulled onto other IT work during the 8 weeks | High | High | Confirm dedicated allocation before kickoff | IT Dept. Head |
| R-02 | D365FO, CUAS, or CNS API access is delayed or limited | Medium | High | Confirm access in Week 1 before development starts | Backend Developer |
| R-03 | Field connectivity issues affect offline sync | Medium | Medium | Build offline-first sync; test with field staff early | Mobile Developer |
| R-04 | Extra feature requests stretch the 8-week scope | Medium | Medium | Keep scope fixed per Section 3; log extra requests for a later phase | Project Manager |
| R-05 | Low field staff adoption after go-live | Medium | Medium | Involve users in UAT; short training before go-live | Marketing Sponsor |
| R-06 | Data entered in the field is incomplete or inconsistent | Medium | Medium | Validation rules and required fields in the app | QA Engineer |

# 11. Communication Plan

| Audience | Frequency | Channel | Content |
| --- | --- | --- | --- |
| Sponsors / Steering | End of each phase | Meeting + short summary | Progress, risks, decisions |
| Marketing Intelligence Officer | Weekly | Meeting / email | Requirement checks, feature reviews |
| Development Team | Daily | Stand-up | Progress and blockers |
| Marketing Department | End of each sprint | Sprint review demo | Working features, feedback |
| Field Staff | Week 8 | Training session | Onboarding before go-live |
| IT Department Head | Bi-weekly | Status update | Resourcing and risks |

# 12. Project Schedule

Assumes a project start of Monday, 6 July 2026, pending Charter approval.

| Milestone | Target Date |
| --- | --- |
| Charter Approved / Kickoff | 6 July 2026 |
| Setup Complete (Week 1) | 10 July 2026 |
| Sprint 1 Complete — Field App & CUAS Login | 24 July 2026 |
| Sprint 2 Complete — Surveys, Media & CNS Notifications | 7 August 2026 |
| Sprint 3 Complete — Pricing Module & Dashboards | 21 August 2026 |
| UAT, Training & Go-Live | 28 August 2026 |

These are planning-level dates. They should be confirmed with the assigned Project Manager once the team is staffed.