IT Department (Solution Development)

Hybrid Market Intelligence System (MIS)

Phase 0 — Project Planning Package

Project Code: KG-MIS-2026-DEV-PROPOSAL

| Field | Detail |
| --- | --- |
| Project Sponsor | Marketing Department, Kerchanshe Group |
| Requesting Officer | Mr. Tsegaye Nigusie — Marketing Intelligence Officer |
| Delivery Owner | IT Department (Solution Development) |
| CTO | Mr. Melkamu Alamerew |
| Project Manager | TBD |
| Developer | Mr. Woluman Urgesa |
| QA/Test Engineer | Mr. Hirko Gemechu |
| Document Status | Draft v1.2 — For Review |
| Prepared Date | 17 July 2026 |

# Table of Contents

Table of Contents	2

1. Project Charter	4

1.1 Purpose	4

1.2 Business Justification	4

1.3 Project Objectives	4

1.4 High-Level Scope	4

1.5 Success Criteria	4

1.6 Timeline & Budget (Indicative)	4

1.7 Authorization	5

2. Business Case	6

2.1 Problem Statement	6

2.2 Proposed Solution	6

2.3 Expected Benefits	6

2.4 Budget Breakdown	6

2.4.1 Labor Cost	6

2.4.2 Infrastructure & Systems	6

2.4.3 Contingency	7

2.4.4 Total Estimated Budget	7

2.5 Risk of Not Proceeding	7

3. Scope Definition	8

3.1 In-Scope	8

3.2 Out-of-Scope (This Release)	8

3.3 Assumptions	8

3.4 Constraints	8

3.5 Phase 0 Deliverables	8

4. Stakeholder Identification	10

5. Team Formation	11

5.1 Project Team	11

5.2 Reporting Structure	11

6. Product Backlog Creation	12

6.1 Epics	12

6.2 Sample User Stories	12

6.3 Backlog Grooming	12

7. Sprint Planning — Sprint 0	13

7.1 Objective	13

7.2 Key Activities	13

7.3 Exit Criteria	13

7.4 Pre-Sprint: React Native Onboarding (2 Weeks)	13

8. Project Plan	14

8.1 Delivery Approach	14

8.2 Phase Overview (10 Weeks)	14

9. Sprint Roadmap	15

10. Risk Register / Risk Assessment	16

11. Communication Plan	17

12. Project Schedule	18

# 1. Project Charter

## 1.1 Purpose

This charter authorizes the Hybrid Market Intelligence System (MIS) project. It confirms delivery using the in-house team's existing skills (Node.js, Next.js, Express, PostgreSQL, TypeScript, React Native), with Power BI for analytics and integration with three internal systems: D365FO (ERP/CRM data), CUAS (role-based access), and CNS (notifications).

## 1.2 Business Justification

Market data — competitor pricing, distributor feedback, and field surveys — is currently collected manually and is hard to consolidate. The MIS will bring this data into one system, connected to the tools the business already uses, so Marketing can act on it faster.

## 1.3 Project Objectives

- Give field teams one app to collect market visit reports, surveys, and photos/videos — including offline.

- Capture and compare competitor pricing against our own.

- Provide Power BI dashboards and simple automated reports.

- Connect to D365FO for customer, sales, and product data.

- Use CUAS for user login and role-based access instead of building this from scratch.

- Use CNS for notifications (email, SMS, WhatsApp).

## 1.4 High-Level Scope

In scope: mobile field data app, web admin portal, survey builder, photo/video capture, competitor pricing module, Power BI dashboards, and integration with D365FO, CUAS, and CNS.

Out of scope for this release: a full CRM replacement, an automated pricing-decision engine, a custom report builder beyond Power BI, and any notification channel other than email, SMS, and WhatsApp (no push or in-app notifications).

## 1.5 Success Criteria

- System is live and field teams are submitting data.

- Power BI dashboards show field and D365FO data correctly.

- Login/access works through CUAS and notifications work through CNS.

- Marketing Department signs off after user acceptance testing.

## 1.6 Timeline & Budget (Indicative)

| Item | Estimate | Notes |
| --- | --- | --- |
| Target Start Date | 20 July 2026 | Pending charter approval |
| Duration | 10 weeks (incl. 2-week React Native onboarding) | See Project Plan, Section 8 |
| Budget | $4,269 | See detailed Budget Breakdown, Section 2.4 |

## 1.7 Authorization

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | Ms. Mekdes Tilahun |  |  |
| CTO | Mr.Melkamu Alamerew |  |  |
| IT Department Head/Manager | Mr. ______________ |  |  |
| Project Manager | TBD________________ |  |  |

# 2. Business Case

## 2.1 Problem Statement

Competitor pricing, distributor feedback, and field survey data are collected manually today. This is slow, inconsistent, and disconnected from D365FO and Power BI, which delays pricing and marketing decisions.

## 2.2 Proposed Solution

A single system for field data collection, competitor pricing, surveys, and reporting — built in-house, connected to D365FO for master data, CUAS for access control, and CNS for notifications.

## 2.3 Expected Benefits

- Faster, more consistent market intelligence reporting.

- Better pricing and marketing decisions from competitor benchmarking.

- One login and access system (CUAS) instead of a separate one for this app.

- Automatic notifications (CNS) instead of manual follow-ups.

- Lower cost and faster delivery by using the in-house team and existing internal systems.

## 2.4 Budget Breakdown

The breakdown below covers all resources needed to deliver the 10-week plan in Section 8. Person-week counts follow the Team Formation in Section 5. Currency amounts are marked TBD for Finance/IT to confirm using actual internal rates; the quantities and structure are fixed so the total can be completed quickly.

## 2.4.1 Labor Cost

| Role | Allocation | Duration | Est. Weekly Rate (USD) | Est. Cost (USD) |
| --- | --- | --- | --- | --- |
| Project Manager | Full-time | 10 weeks | $138 | $1,382 |
| React Native Onboarding & Training | Full-time | 2 weeks | $94 | $188 |
| Requirement Gathering & System Architecture | Full-time | 1 week | $113 | $113 |
| Backend Developer (Node.js/Express) | Full-time | 3 weeks | $126 | $377 |
| Frontend Developer (Next.js) | Full-time | 2 weeks | $113 | $226 |
| Android Developer (React Native) | Full-time | 2 weeks | $113 | $226 |
| QA / Test Engineer (Hirko Gemechu) | Full-time | 2 weeks | $88 | $176 |
| Labor Subtotal |  | 22 person-weeks |  | $2,688 |

## 2.4.2 Infrastructure & Systems

| Item | Notes | Est. Cost (USD) |
| --- | --- | --- |
| Hosting (Development, Staging & Production) | Cloud hosting & PostgreSQL | $377 |
| D365FO Integration | Internal API configuration | $126 |
| CUAS Integration | Authentication integration | $94 |
| CNS Integration | Email, SMS & WhatsApp configuration | $157 |
| Power BI Configuration | Dashboard configuration | $94 |
| Field Test Devices | Smartphones/tablets for testing | $251 |
| Domain, SSL & Development Tools | SSL, domains, miscellaneous tools | $94 |
| Infrastructure Subtotal |  | $1,193 |

## 2.4.3 Contingency

| Item | Basis | Est. Cost (USD) |
| --- | --- | --- |
| Contingency Reserve | 10% of Labor + Infrastructure | $388 |

## 2.4.4 Total Estimated Budget

| Category | Est. Cost (USD) |
| --- | --- |
| Labor Subtotal | $2,688 |
| Infrastructure Subtotal | $1,193 |
| Contingency (10%) | $388 |
| Total Estimated Budget | $4,269 |

## 2.5 Risk of Not Proceeding

Without the MIS, Marketing continues to rely on manual, fragmented data, which slows down pricing and competitor response.

# 3. Scope Definition

## 3.1 In-Scope

- Field data collection: market visit reports, interviews, structured surveys.

- Photo/video capture, linked to surveys and reports.

- Competitor pricing capture and comparison.

- D365FO integration for customer, product, and sales data.

- CUAS integration for login and role-based access (no separate access system built).

- CNS integration for email, SMS, and WhatsApp notifications.

- Power BI dashboards with basic scheduled reports.

## 3.2 Out-of-Scope (This Release)

- Full CRM replacement of D365FO.

- Automated pricing-recommendation engine.

- Custom report builder beyond standard Power BI reports.

- Push notifications and in-app notifications (CNS covers email, SMS, WhatsApp only).

## 3.3 Assumptions

- D365FO, CUAS, and CNS all expose APIs the in-house team can integrate with.

- Field staff have smartphones/tablets that can run the mobile app, including offline use.

## 3.4 Constraints

- The 10-week timeline is fixed, so scope is limited to what the team can deliver in that time.

- Field network connectivity may be unreliable, so the app needs offline support.

## 3.5 Phase 0 Deliverables

| Deliverable | Description |
| --- | --- |
| Project Charter | Objectives and success criteria (Section 1) |
| Business Case | Justification and expected benefits (Section 2) |
| Scope Definition | In/out of scope, assumptions, constraints (Section 3) |
| Stakeholder Identification | Stakeholder list and engagement approach (Section 4) |
| Team Formation | Roles and responsibilities (Section 5) |
| Product Backlog | Initial epics and user stories (Section 6) |
| Sprint Planning | Sprint 0 plan (Section 7) |
| Project Plan | 10-week delivery approach (Section 8) |
| Sprint Roadmap | Sprint-by-sprint plan (Section 9) |
| Risk Register | Key risks and mitigation (Section 10) |
| Communication Plan | Who gets updated, how, and when (Section 11) |
| Project Schedule | Week-by-week milestones (Section 12) |

# 4. Stakeholder Identification

| Stakeholder | Role | Interest | Engagement |
| --- | --- | --- | --- |
| Tsegaye Nigusie | Marketing Intelligence Officer — main requester | Defines requirements, approves features | Weekly check-ins, UAT sign-off |
| Marketing Dept. Management | Sponsor | Budget and strategic alignment | Milestone reviews |
| Chief Technology Officer (CTO) | Executive Sponsor & Technical governance | Strategic oversight, technology alignment, final project approval | Executive milestone reviews and key decision meetings |
| IT Department Head | Delivery oversight | Resourcing, technical approval | Bi-weekly status updates |
| In-house Dev Team | Delivery team | Builds and delivers the system | Daily stand-ups, sprint reviews |
| Field Marketing/Sales Staff | End users | Ease of use, offline reliability | Training and UAT |
| D365FO / CUAS / CNS Owners | Internal systems owners | API access, data integrity, uptime | Joint integration planning in Week 1 |

# 5. Team Formation

## 5.1 Project Team

| Role | Responsibility | Assigned To |
| --- | --- | --- |
| Project Manager | Planning, tracking, stakeholder communication | TBD |
| Backend Developer (Node.js/Express) | API development, business logic, D365FO integration; PostgreSQL schema design, performance, and backups | Woluman Urgesa |
| Frontend Developer (Next.js) | Web admin portal, report builder UI; Power BI dashboard design, KPI modeling, report automation | Woluman Urgesa |
| Mobile Developer (React Native) | Field data collection app, offline sync | Woluman Urgesa |
| QA / Test Engineer | Test planning, functional testing, UAT support | Hirko Gemechu |

## 5.2 Reporting Structure

The Project Manager reports to the IT Department Head and the Marketing Department sponsor. Team members report to the Project Manager for the duration of the project.

# 6. Product Backlog Creation

## 6.1 Epics

| Epic ID | Epic | Priority |
| --- | --- | --- |
| EPIC-01 | Field Data Collection App (offline capture) | High |
| EPIC-02 | Survey & Questionnaire Builder | High |
| EPIC-03 | Photo/Video Capture & Tagging | Medium |
| EPIC-04 | Competitor & Pricing Module | High |
| EPIC-05 | D365FO Integration (customer, sales, product data) | High |
| EPIC-06 | CUAS Integration (login & role-based access) | High |
| EPIC-07 | CNS Integration (email, SMS, WhatsApp notifications) | Medium |
| EPIC-08 | Power BI Dashboards & Basic Reports | High |

## 6.2 Sample User Stories

- As a field officer, I can log a market visit report offline and it syncs when I'm back online.

- As a user, I can log in using my normal company account through CUAS.

- As a marketing manager, I get a WhatsApp or email alert (via CNS) when a new report is submitted.

- As a marketing analyst, I can compare our pricing to competitor pricing on a dashboard.

- As a field officer, I can attach photos to a survey response.

## 6.3 Backlog Grooming

The backlog is reviewed at the end of each sprint, with the Marketing Intelligence Officer involved in prioritization.

# 7. Sprint Planning — Sprint 0

## 7.1 Objective

Sprint 0 sets up the technical foundation before feature development starts. It runs for Week 3 of the 10-week schedule, right after the 2-week React Native onboarding (Section 7.4).

## 7.2 Key Activities

- Confirm architecture: Node.js/Express API, Next.js portal, React Native app, PostgreSQL database.

- Set up development and staging environments and source control.

- Confirm API access for D365FO, CUAS, and CNS.

- Set up the Power BI workspace.

- Groom and estimate the backlog (Section 6).

## 7.3 Exit Criteria

- Environments are ready for all team members.

- D365FO, CUAS, and CNS access is confirmed.

- Backlog is estimated and ready for Sprint 1.

## 7.4 Pre-Sprint: React Native Onboarding (2 Weeks)

Because the mobile stack (React Native/Expo) is newer ground for the team, a dedicated 2-week onboarding runs immediately before Sprint 0. It brings the Mobile Developer and Hirko Gemechu (Co-Developer) up to speed on React Native/Expo, offline-first architecture, and EAS Build, so Sprint 0 and Sprint 1 start on a working mobile foundation rather than a learning curve.

Week 1 – React Native / Expo Fundamentals

- Set up React Native with Expo, project structure, and navigation.

- Review offline-first architecture patterns: local storage, sync queues, and conflict handling.

- Pair Hirko Gemechu onto the mobile codebase and agree on coding standards and Git workflow.

- Build a small proof-of-concept screen (e.g. offline form capture) to validate the approach.

Week 2 – Integration & Build Pipeline

- Configure EAS Build for Android/iOS packaging and app store deployment.

- Connect the app shell to CUAS for authentication and confirm the D365FO/CNS API contracts the mobile app will use.

- Test offline sync end-to-end on a device, including poor-connectivity scenarios.

- Document setup, conventions, and lessons learned for the rest of the team ahead of Sprint 0.

Exit Criteria

- React Native/Expo environment, navigation, and offline-first pattern are working end-to-end in a proof-of-concept.

- EAS Build is configured and produces an installable build.

# 8. Project Plan

## 8.1 Delivery Approach

The project is delivered in one continuous 10-week schedule using short, focused sprints, so the Marketing Department can see progress regularly. The first 2 weeks are a dedicated React Native onboarding period (Section 7.4) so the mobile team is ready before Sprint 0 begins.

## 8.2 Phase Overview (10 Weeks)

| Phase | Objective | Timing |
| --- | --- | --- |
| Onboarding. React Native Mobile Tech Stack | Ramp up on React Native/Expo and offline-first architecture; configure EAS Build; pair Hirko Gemechu onto the mobile codebase | Weeks 1–2 |
| 0. Planning & Setup | Architecture, environments, access to D365FO/CUAS/CNS, backlog ready | Week 3 |
| 1. Core Build | Field app, data model, CUAS login integration | Weeks 4–5 |
| 2. Feature Build | Survey builder, photo/video capture, CNS notifications, D365FO sync | Weeks 6–7 |
| 3. Analytics | Competitor pricing module, Power BI dashboards and reports | Weeks 8–9 |
| 4. Testing & Go-Live | UAT, fixes, training, deployment | Week 10 |

# 9. Sprint Roadmap

| Sprint | Timing | Focus |
| --- | --- | --- |
| Onboarding Sprint | Weeks 1–2 | React Native/Expo ramp-up, offline-first architecture study, EAS Build setup, pairing with Hirko Gemechu |
| Sprint 0 | Week 3 | Requirement, Setup, architecture, access confirmation, backlog |
| Sprint 1 | Weeks 4–5 | Field data app, data model, CUAS login |
| Sprint 2 | Weeks 6–7 | Survey builder, photo/video capture, CNS notifications, D365FO sync |
| Sprint 3 | Weeks 8–9 | Competitor pricing module, Power BI dashboards |
| Final Week | Week 10 | UAT, fixes, training, go-live |

# 10. Risk Register / Risk Assessment

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | Team members are pulled onto other IT work during the 10 weeks | High | High | Confirm dedicated allocation before kickoff | IT Dept. Head |
| R-02 | D365FO, CUAS, or CNS API access is delayed or limited | Medium | High | Confirm access in Week 1 before development starts | Backend Developer |
| R-03 | Field connectivity issues affect offline sync | Medium | Medium | Build offline-first sync; test with field staff early | Mobile Developer |
| R-04 | Extra feature requests stretch the 10-week scope | Medium | Medium | Keep scope fixed per Section 3; log extra requests for a later phase | Project Manager |
| R-05 | Low field staff adoption after go-live | Medium | Medium | Involve users in UAT; short training before go-live | Marketing Sponsor |
| R-06 | Data entered in the field is incomplete or inconsistent | Medium | Medium | Validation rules and required fields in the app | QA Engineer |

# 11. Communication Plan

| Audience | Frequency | Channel | Content |
| --- | --- | --- | --- |
| Sponsors / Steering | End of each phase | Meeting + short summary | Progress, risks, decisions |
| Marketing Intelligence Officer | Weekly | Meeting / email | Requirement checks, feature reviews |
| Development Team | Daily | Stand-up | Progress and blockers |
| Marketing Department | End of each sprint | Sprint review demo | Working features, feedback |
| Field Staff | Week 8 | Training session | Onboarding before go-live |
| IT Department Head | Bi-weekly | Status update | Resourcing and risks |

# 12. Project Schedule

Assumes a project start of Monday, 27 July 2026, pending Charter approval.

| Milestone | Target Date |
| --- | --- |
| Charter Approved / Kickoff | 27 July 2026 |
| React Native Onboarding Complete (Week 2) | 27 Jul – 7 Aug 2026 |
| Setup Complete (Week 3) | 10 Aug – 14 Aug 2026 |
| Sprint 1 Complete — Field App & CUAS Login | 17 Aug – 28 Aug 2026 |
| Sprint 2 Complete — Surveys, Media & CNS Notifications | 31 Aug – 11 Sep 2026 |
| Sprint 3 Complete — Pricing Module & Dashboards | 14 Sep – 25 Sep 2026 |
| UAT, Training & Go-Live | 28 Sep – 2 Oct 2026 |