## Sheet1
Kerchanshe Solutions Development Cycle (Agile Approach)
Phase | Objective | Key Activities | Key Deliverables | Responsible Team
0. Project Planning | Define project scope, resources, timeline, and roadmap | • Project Charter | • Project Charter | Project Manager, Product Owner, Solution Architect
|  | • Business Case | • Project Plan
|  | • Scope Definition | • Sprint Roadmap
|  | • Stakeholder Identification | • Risk Register
|  | • Team Formation | • Communication Plan
• Product Backlog Creation
• Sprint Planning
• Project Schedule
• Risk Assessment
1. Requirement Gathering (Discovery) | Understand business requirements and prioritize features | • Stakeholder Workshops | • Business Requirement Document (BRD) | Business Analyst, Product Owner, Business Users
|  | • User Story Collection | • User Stories
|  | • As-Is Process Analysis | • Product Backlog
|  | • To-Be Process Design | • Process Flow
|  | • Gap Analysis | • Gap Analysis
• Requirement Prioritization
• Acceptance Criteria Definition
2. Solution Design | Design the functional and technical solution | • Functional Design | • Solution Design Document (SDD) | Solution Architect, UI/UX Designer, Technical Lead
|  | • Technical Architecture | • Functional Design Specification (FDS)
|  | • UI/UX Design | • Technical Design Specification (TDS)
|  | • Database Design | • Integration Design
|  | • API & Integration Design | • Security Matrix
• Security Design
• Workflow Design
3. Development (Sprint Execution) | Configure and develop the solution incrementally | • Sprint Planning | • Configured Modules | Developers, Technical Lead
|  | • ERP Configuration | • Source Code
|  | • Coding & Customization | • Reports & Dashboards
|  | • API Development | • APIs
|  | • Dashboard & Report Development | • Unit Test Results
• Daily Stand-up
• Code Review
• Unit Testing
4. Testing & Quality Assurance | Verify solution quality and functionality | • Functional Testing | • Test Cases | QA Team, Developers
|  | • System Integration Testing (SIT) | • Test Results
|  | • Regression Testing | • Defect Log
|  | • Performance Testing | • QA Sign-off
• Security Testing
• Bug Fixing
5. User Acceptance Testing (UAT) | Validate the solution with business users | • UAT Execution | • UAT Sign-off | Business Users, Product Owner, QA
|  | • End-to-End Business Scenarios | • Go-Live Readiness Report
|  | • User Training | • Approved Business Processes
• Issue Resolution
• Business Validation
• Sprint Review & Demo
6. Data Migration & Go-Live | Deploy the solution into production | • Data Cleansing | • Data Migration Report | Data Migration Team, Infrastructure Team, ERP Team
|  | • Data Mapping | • Training Completion Report
|  | • Trial Migration | • Go-Live Checklist
|  | • Final Data Migration | • Production Environment
• Production Deployment
• User Training
• Cutover Activities
7. Post-Implementation Support (Hypercare) | Ensure system stability and continuous improvement | • Production Monitoring | • Hypercare Report | Support Team, ERP Team, Project Manager
|  | • Issue Resolution | • Issue Log
|  | • Performance Optimization | • Support Handover Document
|  | • Knowledge Transfer | • Project Closure Report
• Documentation Update
• Transition to Support Team
Agile Governance
Ceremony | Frequency | Purpose
Sprint Planning | Beginning of Every Sprint | Plan sprint backlog and objectives
Daily Stand-up | Daily (15 Minutes) | Track progress and resolve blockers
Backlog Refinement | Weekly | Prioritize and refine user stories
Sprint Review / Demo | End of Every Sprint | Demonstrate completed functionality
Sprint Retrospective | End of Every Sprint | Identify lessons learned and improvements
Release Planning | Before Each Release | Prepare for deployment and production readiness
Continuous Integration (CI) | Continuous | Integrate code frequently
Continuous Testing (CT) | Continuous | Validate quality throughout development
Continuous Deployment (CD) | As Required | Deploy approved releases efficiently